## Sheet1
| 2014 | [6 empty] | 2015
Task | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb
Finish disparity analysis | bar: 2014 Jun
Finish the disparity draft | bar: 2014 Jun to 2014 Jul
Summer conferences | bar: 2014 Jun to 2014 Jul
Submit the disparity paper | bar: 2014 Aug
Collect ecological data | bar: 2014 Jul to 2014 Sep
Finish thesis chapter 2 (data collection) | bar: 2014 Aug to 2014 Sep
Morphological convergence analysis | bar: 2014 Sep to 2014 Nov
Write the 2nd paper (morphological convergence) | [9 empty] | Key | bar: 2014 Nov to 2014 Dec
Submit the 2nd paper | [9 empty] | Analysis | bar: 2015 Jan
Analyse ecological data | [9 empty] | Paper writing | bar: 2015 Jan to 2015 Feb
Write the 3rd paper (morphological vs. ecological convergence) | [9 empty] | Paper submission | bar: 2015 Feb
| 2014 Jun: 2015 | Conferences
Task | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Data collection
Write the 3rd paper (continued) | [9 empty] | Thesis writing | bar: 2015 Mar
Submit the 3rd paper | [9 empty] | Thesis submission | bar: 2015 Apr
Write the 4th paper (review of convergence methods) | bar: 2015 Apr to 2015 May
Thesis chapter 3 (disparity, paper 1) | bar: 2015 May to 2015 Jun
Submit the 4th paper | bar: 2015 Jun
Summer conferences? | bar: 2015 Jun to 2015 Jul
Thesis chapter 5 (morphological convergence, paper 2) | bar: 2015 Jul to 2015 Aug
Thesis chapter 6 (morphological vs. ecological convergence, paper 3) | bar: 2015 Aug to 2015 Sep
Thesis chapter 4 (review of convergence methods, paper 4) | bar: 2015 Aug to 2015 Sep
Thesis chapters 1 and 7 (introduction and conclusions) | bar: 2015 Oct to 2015 Nov
Submit thesis | bar: 2015 Nov

## Sheet2
Task | Sep | Oct | Nov | Dec | Jan
Finish disparity paper: introduction and discussion | [5 empty] | Key
Submit disparity paper | [5 empty] | Analysis
Convergence analysis | [5 empty] | Paper writing
Morphometric error checking | [5 empty] | Paper submission
Write up convergence methods and results | [5 empty] | Thesis writing
Introduction | [5 empty] | Thesis submission
Discussion
Complete thesis draft
Submit thesis